## Execution Report
QA Status Report DD/MM/YYYY
Release ID | S.No | Story ID/Description | Status | Test Case Count
24.02.01 | 1 | RAIN -5 | Done | 8
|  |  | FAIL | 5
24.04.01 | 2 | MAK -2 | Done | 13
|  |  | Total | 26
Test case Status | No: of Test Case
Pass | 21
Fail | 5
In Progress | 0
Blocked | 0
Not Executed | 0
Not Applicable | 0
Total | 26

## Bug Report
Bug Report
Release ID | Sprint # | User Story ID | Wrong validation message is displayed when name field is entered with special character in the my profile page. | Bug Summary | Severity | Priority | Status | Workaround | Bug Assigned to | Bug Reported by
24.02.01 | Sprint 1 | RAIN-5 | RAIN-223 | Global product search bar and drop down box is overlapping | S3 | P3 | New | NO | ANANDU A | NEENA
|  |  | RAIN-224 | Wrong validation message displayed for searching invalid grocery product | S3 | P3 | Active | NO | ANANDU A | NEENA
|  |  | RAIN-225 | Same validation message displayed for searching invalid and out of stock product | S3 | P3 | closed | NO | ANANDU A | NEENA
|  |  | RAIN-226 | Recent searches are shown at last of the search history | S2 | P2 | Rejected | NO | ANANDU A | NEENA
|  |  | RAIN-227 | search history is shown even after deleting the entry | S1 | P1 | Ready to test | NO | ANANDU A | NEENA
Severity | Bug Count |  |  |  |  | Bug Status | Bug Count
Showstopper | 0 |  |  |  |  | New | 1
Critical | 0 |  |  |  |  | Active | 1
Major | 1 |  |  |  |  | Ready to Test | 1
High | 1 |  |  |  |  | Closed | 1
Low | 3 |  |  |  |  | Re-Open | 0
Total Bugs | 5 |  |  |  |  | Rejected | 0
[6 empty] | Total | 4